## TeamD - Product Backlog (1).tsv
Title | URL | Milestone | Deliverable / Sprint | User Story | Story Type | Priority | Estimate (Story Points) | Status | Contributors and % contribution
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 5> | https://github.com/COS420-F25/TeamD/issues/171 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Develop 3 Automated Tests for Feature 2 | https://github.com/COS420-F25/TeamD/issues/133 |  | D4 |  | Technical work | High | 3 | Done | 100%
Develop Feature 2: Profile Customization | https://github.com/COS420-F25/TeamD/issues/131 |  | D4 |  | Technical work | High | 5 | Done | 100%
Sprint Review D5 | https://github.com/COS420-F25/TeamD/issues/187 |  | D5 |  |  | High |  | Done
Create Example of Applying Design Pattern (description) <Feature 4> | https://github.com/COS420-F25/TeamD/issues/174 |  | D4 |  | Technical work | High | 1 | Done | 100%
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 4> | https://github.com/COS420-F25/TeamD/issues/170 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 6> | https://github.com/COS420-F25/TeamD/issues/168 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Create Example of Applying Design Pattern (description) <Feature 6> | https://github.com/COS420-F25/TeamD/issues/172 |  | D4 |  | Non-technical | High | 1 | Done | 100%
<Website Navigation> (Set up Dummy pages) | https://github.com/COS420-F25/TeamD/issues/155 |  | D4 |  | Technical work | High | 4 | Done | 100%
Create list of Objects for Domain Model (Like the bottom page of linked examples) | https://github.com/COS420-F25/TeamD/issues/126 |  | D3 |  | Non-technical | High | 2 | Done | 100%
Set up Meeting with Dr Greg for project scoping | https://github.com/COS420-F25/TeamD/issues/144 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Sprint Review D4 | https://github.com/COS420-F25/TeamD/issues/147 |  | D4 |  | Non-technical | High | 2 | Done | 20% each
Develop 3 Automated Tests for Feature 1 | https://github.com/COS420-F25/TeamD/issues/132 |  | D3 |  | Technical work | High | 3 | Done | 100%
Design Pattern for Design Technical Design | https://github.com/COS420-F25/TeamD/issues/189 |  | D5 |  |  | High |  | Done
Create Example of Applying Design Pattern (description) <Feature 5> | https://github.com/COS420-F25/TeamD/issues/175 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 3> | https://github.com/COS420-F25/TeamD/issues/169 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Finish Feature 1 <Github Linking> | https://github.com/COS420-F25/TeamD/issues/164 |  | D4 |  | Technical work | High | 3 | Done | Mason (20%), Josh (80%)
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 1> | https://github.com/COS420-F25/TeamD/issues/153 |  | D4 |  | Non-technical | High | 2 | Done | 100%
Create Example of Applying Design Pattern (description) <Feature 1> | https://github.com/COS420-F25/TeamD/issues/152 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Develop Feature 1: Git Integration | https://github.com/COS420-F25/TeamD/issues/130 |  | D3 |  | Technical work | High | 5 | Done | Mason (20%), Josh (80%)
Assign Tasks | https://github.com/COS420-F25/TeamD/issues/154 |  | D4 |  | Non-technical | High | 1 | Done | Mason (80%), 20% everyone else
Record 1-10 Minute Demo Video of our App Progress <FEATURE 1> | https://github.com/COS420-F25/TeamD/issues/137 |  | D3 |  | Non-technical | High | 2 | Done | 100%
Fix Figures in Deliverable 1 | https://github.com/COS420-F25/TeamD/issues/55 |  | D1 |  | Non-technical | High | 1 | Done
System Requirements Specification | https://github.com/COS420-F25/TeamD/issues/40 |  | D1 |  | Non-technical | High | 5 | Done
Build work environment, screenshot your website working and add it to Google Doc | https://github.com/COS420-F25/TeamD/issues/54 |  | D1 |  | Non-technical | High | 1 | Done
Bring this into Projects. | https://github.com/COS420-F25/TeamD/issues/37 |  | D1 |  | Non-technical | High | 1 | Done
Create Sprint Backlog 1 | https://github.com/COS420-F25/TeamD/issues/36 |  | D1 |  | Non-technical | High | 2 | Done
Add non-technical stories | https://github.com/COS420-F25/TeamD/issues/43 |  | D1 |  | Non-technical | High | 1 | Done
Revise User story document | https://github.com/COS420-F25/TeamD/issues/34 |  | D1 | No | Non-technical | High | 1 | Done
Create Product Backlog | https://github.com/COS420-F25/TeamD/issues/35 |  | D1 |  | Non-technical | High | 1 | Done
Decide & add committed user stories | https://github.com/COS420-F25/TeamD/issues/42 |  | D1 |  | Non-technical | High | 1 | Done
functional requirements 1-10 | https://github.com/COS420-F25/TeamD/issues/44 |  | D1 |  | Non-technical | High | 1 | Done
functional requirements 11-20 | https://github.com/COS420-F25/TeamD/issues/45 |  | D1 |  | Non-technical | High | 1 | Done
non-functional requirements (15) | https://github.com/COS420-F25/TeamD/issues/47 |  | D1 |  | Non-technical | High | 1 | Done
functional requirements 21-30 | https://github.com/COS420-F25/TeamD/issues/46 |  | D1 |  | Non-technical | High | 1 | Done
Sprint Review | https://github.com/COS420-F25/TeamD/issues/39 |  | D1 |  | Non-technical | High | 1 | Done
Discuss features to write requirements on | https://github.com/COS420-F25/TeamD/issues/48 |  | D1 |  | Non-technical | High | 1 | Done
Create READ-ME File | https://github.com/COS420-F25/TeamD/issues/49 |  | D1 |  | Non-technical | High | 1 | Done
Set up build environment | https://github.com/COS420-F25/TeamD/issues/50 |  | D1 |  | Technical work | High | 1 | Done
Software | https://github.com/COS420-F25/TeamD/issues/41 |  | D1 |  | Technical work | High | 1 | Done
LOOK AT FEEDBACK *IMPORTANT* | https://github.com/COS420-F25/TeamD/issues/32 |  | D1 |  | Knowledge acquisition | High | 1 | Done
As a user, I want to link my github account to my profile for a more detailed overview of my work so employers can verify my coding activity and see the full scope of my technical contributions without me manually documenting everything. | https://github.com/COS420-F25/TeamD/issues/60 |  |  | Yes | Technical work | High | 3 | Product Backlog
As a user, I want to generate a shareable link to my profile, so I can include it in job applications, social media profiles, and email signatures without requiring recipients to create an account. | https://github.com/COS420-F25/TeamD/issues/70 |  |  | Yes | Technical work | High | 2 | Product Backlog
As a user, I want to showcase my AI proficiency and methods with annotations on code and tags of projects, so that employers can see how and when I used AI to enhance my work. | https://github.com/COS420-F25/TeamD/issues/81 |  |  | Yes | Technical work | High | 5 | Product Backlog
As a user, I want to be able to set my job-seeking status, so that employers only contact me when looking for employment. | https://github.com/COS420-F25/TeamD/issues/84 |  |  | Yes | Technical work | High | 2 | Product Backlog
As a user, I want to annotate sections of my portfolio projects that were created or improved with AI tools like GitHub Copilot or ChatGPT, so that employers can see specific examples of how I leverage AI in my workflow. | https://github.com/COS420-F25/TeamD/issues/90 |  |  | Yes | Technical work | High | 5 | Product Backlog
As a user, I want to include a section in my portfolio to showcase my AI prompt engineering techniques and the outcomes of different prompts, so employers can assess my creativity and skill in directing generative AI to solve problems. | https://github.com/COS420-F25/TeamD/issues/92 |  |  | Yes | Technical work | High | 5 | Product Backlog
As a user, I want to use my email to login so that I may connect with potential employers. | https://github.com/COS420-F25/TeamD/issues/61 |  |  | Yes | Technical work | High | 3 | Product Backlog
Setup Database (Coding) (First) | https://github.com/COS420-F25/TeamD/issues/107 |  | D2 |  | Technical work | High | 2 | Done
Create Use Case Diagrams (Do these before Use Case Descriptions) | https://github.com/COS420-F25/TeamD/issues/104 |  | D2 |  | Non-technical | High | 3 | Done
Discuss list of objects for domain model | https://github.com/COS420-F25/TeamD/issues/136 |  | D3 |  | Technical work | High | 1 | Done | 20% each
Sprint Review | https://github.com/COS420-F25/TeamD/issues/121 |  | D3 |  | Non-technical | High | 2 | Done | Xander (80%) 20% for everyone else.
Create Design class/function diagram (Quality Check DCD document After completed) | https://github.com/COS420-F25/TeamD/issues/150 |  | D4 |  | Non-technical | High | 2 | Done | 100%
Create Example of Applying Design Pattern (description) <Feature 3> | https://github.com/COS420-F25/TeamD/issues/173 |  | D4 |  | Non-technical | High | 1 | Done | 100%
Record Team Progress Video | https://github.com/COS420-F25/TeamD/issues/159 |  | D4 |  | Non-technical | High | 2 | Done | 100%
Finish Feature Search | https://github.com/COS420-F25/TeamD/issues/197 |  | D5 |  |  | High |  | Done
Finish Feature Profile System | https://github.com/COS420-F25/TeamD/issues/190 |  | D5 |  |  | High |  | Done
Splice videos for progress video | https://github.com/COS420-F25/TeamD/issues/193 |  | D5 |  |  | High |  | Todo / Sprint Backlog
Work on website UI and design (match to our mockups) | https://github.com/COS420-F25/TeamD/issues/194 |  | D5 |  |  | High |  | Quality Checking
Resume Video | https://github.com/COS420-F25/TeamD/issues/198 |  | D5 |  |  | Medium |  | Quality Checking
Develop Feature 3 <Resume System> | https://github.com/COS420-F25/TeamD/issues/166 |  | D5 |  | Technical work | Medium | 4 | Quality Checking | 100%
Finish Feature Resume System | https://github.com/COS420-F25/TeamD/issues/191 |  | D5 |  |  | Medium |  | Quality Checking
Add deliverable documents to Repository | https://github.com/COS420-F25/TeamD/issues/143 |  | D4 |  | Non-technical | Medium | 1 | Done | 20% each
Develop Feature 5 <List/Search/Filter Portfolios> | https://github.com/COS420-F25/TeamD/issues/167 |  | D4 |  | Technical work | Medium | 4 | Done | 100%
Assign sub tasks for DCD Features (After Scoping Meeting) | https://github.com/COS420-F25/TeamD/issues/151 |  | D4 |  | Non-technical | Medium | 1 | Done | 20% each
Record Video Progress for Feature 3 | https://github.com/COS420-F25/TeamD/issues/157 |  | D4 |  | Non-technical | Medium | 2 | Done | 100%
Develop Feature 4 <Tagging System> | https://github.com/COS420-F25/TeamD/issues/165 |  | D4 |  | Technical work | Medium | 4 | Done | 100%
Update ReadMe with new instructions for Feature 1 implementation | https://github.com/COS420-F25/TeamD/issues/142 |  | D3 |  | Non-technical | Medium | 1 | Done | 100%
Create 2-3 Automated Tests for Feature 3 | https://github.com/COS420-F25/TeamD/issues/162 |  | D4 |  | Technical work | Medium | 2 | Done | 100%
Fill In description for Domain Model (After Issues 126/127) | https://github.com/COS420-F25/TeamD/issues/128 |  | D3 |  | Non-technical | Medium | 2 | Done | 100%
Create Diagram for Domain Model (Once Task 126 is finished) | https://github.com/COS420-F25/TeamD/issues/127 |  | D3 |  | Non-technical | Medium | 2 | Done | 100%
Remove Dead Branch <update-readme> from TeamD Project | https://github.com/COS420-F25/TeamD/issues/140 |  | D3 |  | Non-technical | Medium | 1 | Done | 100%
Remove Dead Branch <react-app-setup> from TeamD project | https://github.com/COS420-F25/TeamD/issues/139 |  | D3 |  | Non-technical | Medium | 1 | Done | 100%
Fix YourApp description based on feedback from Deliverable 0 | https://github.com/COS420-F25/TeamD/issues/56 |  | D1 | No | Non-technical | Medium | 1 | Done
As a user, I want to create an appealing portfolio of my work so that it may be seen by potential employers. | https://github.com/COS420-F25/TeamD/issues/62 |  |  | Yes | Technical work | Medium | 8 | Product Backlog
As a user, I want to be able to tag my profile and work, so that it may be easily filtered by potential employers | https://github.com/COS420-F25/TeamD/issues/65 |  |  | Yes | Technical work | Medium | 3 | Product Backlog
As an employer, I want to be able to contact potential employees through their profiles. | https://github.com/COS420-F25/TeamD/issues/68 |  |  | Yes | Technical work | Medium | 5 | Product Backlog
As a user, I want a persistent navigation menu with clear labels like 'My Portfolio,' 'Browse Candidates,' and 'Settings,' so I can access key features without hunting for them. | https://github.com/COS420-F25/TeamD/issues/78 |  |  | Yes | Technical work | Medium | 2 | Product Backlog
As a user, I want to be able to include my achievement highlights, so that non-technical recruiters can understand my accomplishments. | https://github.com/COS420-F25/TeamD/issues/80 |  |  | Yes | Technical work | Medium | 3 | Product Backlog
As a user, I want to track the performance of my portfolio (i.e. views, shares) so that I can gauge interest and adjust my portfolio accordingly. | https://github.com/COS420-F25/TeamD/issues/82 |  |  | Yes | Technical work | Medium | 5 | Product Backlog
As a user, I want to annotate sections of my portfolio projects that were created or improved with AI tools like GitHub Copilot, or ChatGPT, so that employers can see specific examples of how I leverage AI in my workflow. | https://github.com/COS420-F25/TeamD/issues/86 |  |  | Yes | Technical work | Medium | 5 | Product Backlog
As a user, I want to display before and after code samples for key tasks, showing how A generated suggestions improved my solutions, so employers can evaluate my ability to apply and validate AI outputs. | https://github.com/COS420-F25/TeamD/issues/91 |  |  | Yes | Technical work | Medium | 5 | Product Backlog
Mockup 3 | https://github.com/COS420-F25/TeamD/issues/115 |  | D2 |  | Non-technical | Medium | 2 | Done
Mockup 4 | https://github.com/COS420-F25/TeamD/issues/116 |  | D2 |  | Non-technical | Medium | 2 | Done
Mockup 2 | https://github.com/COS420-F25/TeamD/issues/114 |  | D2 |  | Non-technical | Medium | 2 | Done
Mockup 1 | https://github.com/COS420-F25/TeamD/issues/113 |  | D2 |  | Non-technical | Medium | 2 | Done
Setup Continuous Integration for Team D GitHub Repo | https://github.com/COS420-F25/TeamD/issues/129 |  | D3 |  | Technical work | Medium | 2 | Done | 100%
Create 2-3 Automated Tests for Feature 6 | https://github.com/COS420-F25/TeamD/issues/179 |  | D5 |  |  | Medium | 2 | Quality Checking | 100%
Search Video | https://github.com/COS420-F25/TeamD/issues/200 |  | D5 |  |  | Medium |  | Done
Tagging Video | https://github.com/COS420-F25/TeamD/issues/201 |  | D5 |  |  | Medium |  | Done
Develop Feature 6 <Portfolio System> | https://github.com/COS420-F25/TeamD/issues/180 |  | D5 |  |  | Medium | 4 | Done | 100%
Finish Feature Tagging System | https://github.com/COS420-F25/TeamD/issues/192 |  | D5 |  |  | Medium |  | Quality Checking
Profile Video | https://github.com/COS420-F25/TeamD/issues/199 |  | D5 |  | Non-technical | Medium |  | Todo / Sprint Backlog
Update/Revise Sprint Backlog | https://github.com/COS420-F25/TeamD/issues/146 |  | D4 |  | Non-technical | Low | 2 | Done | 100%
Next Round of Usability Tests *****Extra Credit***** | https://github.com/COS420-F25/TeamD/issues/161 |  | D4 |  | Non-technical | Low | 2 | Done | 100% Chauncey
Update/Revise Product Backlog | https://github.com/COS420-F25/TeamD/issues/145 |  | D4 |  | Non-technical | Low | 1 | Done | 100%
Update/Revise Domain Model Description and Object List | https://github.com/COS420-F25/TeamD/issues/149 |  | D4 |  | Non-technical | Low | 1 | Done | Mason (50%), Xander (50%)
Update/Revise Domain Model Diagram | https://github.com/COS420-F25/TeamD/issues/148 |  | D4 |  | Non-technical | Low | 1 | Done | Mason (50%), Xander (50%)
Revise Detailed Technical Design Document | https://github.com/COS420-F25/TeamD/issues/188 |  | D5 |  |  | Low |  | Done
Update Product Backlog | https://github.com/COS420-F25/TeamD/issues/119 |  | D3 |  | Non-technical | Low | 1 | Done | 100%
Update/Revise Architecture Design Document | https://github.com/COS420-F25/TeamD/issues/125 |  | D3 |  | Non-technical | Low | 2 | Done | 100%
Update/Revise SRS Document | https://github.com/COS420-F25/TeamD/issues/122 |  | D3 |  | Non-technical | Low | 2 | Done | 100%
Complete Usability Testing Script | https://github.com/COS420-F25/TeamD/issues/135 |  | D3 |  | Non-technical | Low | 2 | Done | 100%
Update Sprint Backlog | https://github.com/COS420-F25/TeamD/issues/120 |  | D3 |  | Non-technical | Low | 1 | Done | 100%
Update/Revise Use Case Descriptions (After Use Case Diagrams) | https://github.com/COS420-F25/TeamD/issues/124 |  | D3 |  | Non-technical | Low | 2 | Done | 100%
3 Usability Tests | https://github.com/COS420-F25/TeamD/issues/138 |  | D3 |  | Technical work | Low | 2 | Done | 100%
Begin Work on UI (Coding) | https://github.com/COS420-F25/TeamD/issues/105 |  | D2 |  | Technical work | Low | 3 | Done
Create 5 Use Cases | https://github.com/COS420-F25/TeamD/issues/111 |  | D2 |  | Non-technical | Low | 3 | Done
Architecture Design | https://github.com/COS420-F25/TeamD/issues/103 |  | D2 |  | Non-technical | Low | 3 | Done
Revise Requirements and Unique REQ IDs | https://github.com/COS420-F25/TeamD/issues/98 |  | D2 |  | Non-technical | Low | 1 | Done
Fix Non-Functional Requirements | https://github.com/COS420-F25/TeamD/issues/110 |  | D2 |  | Non-technical | Low | 2 | Done
Expand AI Proficiency Features, make sure we have 5 User stories on this | https://github.com/COS420-F25/TeamD/issues/53 |  |  | No | Requirements | Low |  | Done
As an employer, I want to filter candidates by programming languages, years of experience, and university, so I can quickly find candidates with relevant technical backgrounds. | https://github.com/COS420-F25/TeamD/issues/63 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As an employer, I want to be able to create a company profile to illustrate my company’s purpose and values. | https://github.com/COS420-F25/TeamD/issues/64 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As a user, I want to be able to showcase working demos of what I have created, so that examples of my work may be easily viewed. | https://github.com/COS420-F25/TeamD/issues/66 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As a user, I want to be able to customize my profile URL so that it may be easier to remember and appear more professional. | https://github.com/COS420-F25/TeamD/issues/67 |  |  | Yes | Technical work | Low | 3 | Product Backlog
As a user, I want to be able to follow others on the platform, so that I can build my professional network. | https://github.com/COS420-F25/TeamD/issues/69 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As a user, I want to show different portfolios for different purposes, so I can emphasize backend work when applying to infrastructure roles and emphasize design when applying to frontend roles. | https://github.com/COS420-F25/TeamD/issues/71 |  |  | Yes | Technical work | Low | 8 | Product Backlog
As a user, I want to be able to view other users' portfolios, so I can see examples and what my peers are working on. | https://github.com/COS420-F25/TeamD/issues/72 |  |  | Yes | Technical work | Low | 2 | Product Backlog
As a user, I want to change how my portfolio is displayed, so I can emphasize my strongest work first and create a professional impression. | https://github.com/COS420-F25/TeamD/issues/73 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As a user, I want to see the number of profile views, project clicks, and employer saves on my portfolio, so I can understand which projects attract the most attention. | https://github.com/COS420-F25/TeamD/issues/74 |  |  | Yes | Technical work | Low | 8 | Product Backlog
As an employer, I want to be able to filter my search, so I can narrow down potential employees. | https://github.com/COS420-F25/TeamD/issues/75 |  |  | Yes | Technical work | Low | 3 | Product Backlog
As an employer, I want portfolios to load quickly, so I can spend more time looking through candidates. | https://github.com/COS420-F25/TeamD/issues/76 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As an employer, I want to be able to quickly view basic information about a candidate, such as contact, name, or skillset. | https://github.com/COS420-F25/TeamD/issues/77 |  |  | Yes | Technical work | Low | 3 | Product Backlog
As a user, I want to be able to look through employers on the site and send them my portfolio. | https://github.com/COS420-F25/TeamD/issues/79 |  |  | Yes | Technical work | Low | 3 | Product Backlog
As a user, I want to be able to organize my projects into different categories, so that employers can more easily find projects relevant to their interests. | https://github.com/COS420-F25/TeamD/issues/83 |  |  | Yes | Technical work | Low | 3 | Product Backlog
As an employer, I want to be able to see when users were last active or last updated their work, so I know what candidates are using up to date information or are likely to respond. | https://github.com/COS420-F25/TeamD/issues/85 |  |  | Yes | Technical work | Low | 3 | Product Backlog
As a user, I want to display before and after code samples for key tasks, showing how A generated suggestions improved my solutions, so employers can evaluate my ability to apply and validate AI outputs. | https://github.com/COS420-F25/TeamD/issues/87 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As a user, I want to include a section in my portfolio to showcase my AI prompt engineering techniques and the outcomes of different prompts, so employers can assess my creativity and skill in directing generative AI to solve problems. | https://github.com/COS420-F25/TeamD/issues/88 |  |  | Yes | Technical work | Low | 5 | Product Backlog
As an employer, I want to filter and search candidate portfolios by demonstrating use of AI skills or tools such as prompt engineering, Copilot, or API usage, so I can easily identify candidates with relevant AI capabilities for my company’s needs. | https://github.com/COS420-F25/TeamD/issues/89 |  |  | Yes | Technical work | Low | 3 | Product Backlog
As an employer, I want to filter and search candidate portfolios by demonstrating use of AI skills or tools such as prompt engineering, Copilot, or API usage, so I can easily identify candidates with relevant AI capabilities for my company’s needs. | https://github.com/COS420-F25/TeamD/issues/93 |  |  | Yes | Technical work | Low | 5 | Product Backlog
Add descriptions from rubric to each task | https://github.com/COS420-F25/TeamD/issues/94 |  | D1 | No | Non-technical | Low |  | Done
Fix yourApp description from D0 | https://github.com/COS420-F25/TeamD/issues/96 |  | D2 |  | Non-technical | Low | 1 | Done
Fix User Stories | https://github.com/COS420-F25/TeamD/issues/97 |  | D2 |  | Non-technical | Low | 1 | Done
Revise Mockups 3 and 4 | https://github.com/COS420-F25/TeamD/issues/118 |  | D2 |  | Non-technical | Low | 2 | Done
Fix Sprint Review | https://github.com/COS420-F25/TeamD/issues/99 |  | D2 |  | Non-technical | Low | 2 | Done
Fill out the rest of the SRS | https://github.com/COS420-F25/TeamD/issues/102 |  | D2 |  | Non-technical | Low | 5 | Done
Create 5 Use Cases | https://github.com/COS420-F25/TeamD/issues/112 |  | D2 |  | Non-technical | Low | 3 | Done
Creating Classes (Coding) | https://github.com/COS420-F25/TeamD/issues/106 |  | D2 |  | Non-technical | Low | 3 | Done
Create description under diagram | https://github.com/COS420-F25/TeamD/issues/109 |  | D2 |  | Non-technical | Low | 1 | Done
UI Mockups | https://github.com/COS420-F25/TeamD/issues/101 |  | D2 |  | Non-technical | Low | 3 | Done
Sprint Review | https://github.com/COS420-F25/TeamD/issues/100 |  | D2 |  | Non-technical | Low | 1 | Done
Revise Mockups 1 and 2 | https://github.com/COS420-F25/TeamD/issues/117 |  | D2 |  | Non-technical | Low | 2 | Done
Description For document | https://github.com/COS420-F25/TeamD/issues/108 |  | D2 |  | Non-technical | Low | 2 | Done
Create Quality checking policy within wiki | https://github.com/COS420-F25/TeamD/issues/95 |  | D2 |  | Non-technical | Low | 1 | Done
Update/Revise Use Case Diagrams (Before Use Case Descriptions) | https://github.com/COS420-F25/TeamD/issues/123 |  | D3 |  | Non-technical | Low | 2 | Done | 100%
Update/Revise Product Backlog | https://github.com/COS420-F25/TeamD/issues/185 |  | D5 |  |  | Low |  | Todo / Sprint Backlog
Update/Revise Sprint Backlog | https://github.com/COS420-F25/TeamD/issues/186 |  | D5 |  |  | Low |  | Todo / Sprint Backlog
Test Plan ****EXTRA CREDIT**** | https://github.com/COS420-F25/TeamD/issues/195 |  | D5 |  |  | Low |  | Todo / Sprint Backlog
Usability Testing ****EXTRA CREDIT**** | https://github.com/COS420-F25/TeamD/issues/196 |  | D5 |  |  | Low |  | Todo / Sprint Backlog