## TeamD - Sprint Backlog
Title | URL | Status | Priority | Story Type | Estimate (Story Points) | Points Completed | Assignees | Contributors and % contribution | Quality Reviewer | Start date | End date (ready for QC by) | Deliverable / Sprint
Fix Figures in Deliverable 1 | https://github.com/COS420-F25/TeamD/issues/55 | Done | High | Non-technical | 1 | 1 | ChaunceyCon |  | Mason P | 2025-10-06 |  | D1
Build work environment, screenshot your website working and add it to Google Doc | https://github.com/COS420-F25/TeamD/issues/54 | Done | High | Non-technical | 1 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 |  | Chauncy O | 2025-10-06 |  | D1
Bring this into Projects. | https://github.com/COS420-F25/TeamD/issues/37 | Done | High | Non-technical | 1 |  | ChaunceyCon |  | Josh V | 2025-10-06 |  | D1
Create Sprint Backlog 1 | https://github.com/COS420-F25/TeamD/issues/36 | Done | High | Non-technical | 2 | 1 | ChaunceyCon |  | Xander W | 2025-10-06 |  | D1
System Requirements Specification | https://github.com/COS420-F25/TeamD/issues/40 | 10-30% done | High | Non-technical | 5 |  | ChaunceyCon |  | Nathan E | 2025-10-06 |  | D1
Add non-technical stories | https://github.com/COS420-F25/TeamD/issues/43 | Done | High | Non-technical | 1 | 1 | NathHayes |  | Chauncy O | 2025-10-06 | 2025-10-13 | D1
Revise User story document | https://github.com/COS420-F25/TeamD/issues/34 | Done | High | Non-technical | 1 |  | Peazlez |  | Josh V | 2025-10-06 |  | D1
Create Product Backlog | https://github.com/COS420-F25/TeamD/issues/35 | Done | High | Non-technical | 1 | 1 | Peazlez |  | Xander W | 2025-10-06 |  | D1
Decide & add committed user stories | https://github.com/COS420-F25/TeamD/issues/42 | Done | High | Non-technical | 1 | 1 | PineCubed |  | Nathan E | 2025-10-06 |  | D1
functional requirements 1-10 | https://github.com/COS420-F25/TeamD/issues/44 | Done | High | Non-technical | 1 | 1 | Peazlez |  | Mason P | 2025-10-06 |  | D1
functional requirements 11-20 | https://github.com/COS420-F25/TeamD/issues/45 | Done | High | Non-technical | 1 | 1 | Xyrox47 |  | Chauncy O | 2025-10-06 |  | D1
non-functional requirements (15) | https://github.com/COS420-F25/TeamD/issues/47 | Done | High | Non-technical | 1 | 1 | Xyrox47 |  | Mason P | 2025-10-06 |  | D1
functional requirements 21-30 | https://github.com/COS420-F25/TeamD/issues/46 | In Progress | High | Non-technical | 1 |  | NathHayes |  | Xander W | 2025-10-06 |  | D1
Sprint Review | https://github.com/COS420-F25/TeamD/issues/39 | In Progress | High | Non-technical | 1 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 |  | Nathan E | 2025-10-06 |  | D1
Discuss features to write requirements on | https://github.com/COS420-F25/TeamD/issues/48 | Done | High | Non-technical | 1 | 1 | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 |  | Josh V | 2025-10-06 |  | D1
Create READ-ME File | https://github.com/COS420-F25/TeamD/issues/49 | Done | High | Non-technical | 1 | 1 | PineCubed |  | Chauncy O | 2025-10-06 |  | D1
Set up build environment | https://github.com/COS420-F25/TeamD/issues/50 | Done | High | Technical work | 1 | 1 | PineCubed |  | Mason P | 2025-10-06 |  | D1
Software | https://github.com/COS420-F25/TeamD/issues/41 | Done | High | Technical work | 1 | 1 | Peazlez |  | Xander W | 2025-10-06 |  | D1
LOOK AT FEEDBACK *IMPORTANT* | https://github.com/COS420-F25/TeamD/issues/32 | Done | High | Knowledge acquisition | 1 | 1 | Peazlez |  | Nathan E | 2025-10-06 |  | D1
Fix YourApp description based on feedback from Deliverable 0 | https://github.com/COS420-F25/TeamD/issues/56 | Done | Medium | Non-technical | 1 | 1 | NathHayes |  | Josh V | 2025-10-06 |  | D1
Add descriptions from rubric to each task | https://github.com/COS420-F25/TeamD/issues/94 | Done | Low | Non-technical | 1 |  | Peazlez |  | Josh V | 2025-10-06 |  | D1
Setup Database (Coding) (First) | https://github.com/COS420-F25/TeamD/issues/107 | Done | High | Technical work | 2 |  | Xyrox47 |  | Nathan H | 2025-10-17 | 2025-10-23 | D2
Create Use Case Diagrams (Do these before Use Case Descriptions) | https://github.com/COS420-F25/TeamD/issues/104 | Done | High | Non-technical | 3 |  | NathHayes |  | Xander W | 2025-10-17 | 2025-10-23 | D2
Mockup 3 | https://github.com/COS420-F25/TeamD/issues/115 | Done | Medium | Non-technical | 2 |  | Xyrox47 |  | Chauncy O | 2025-10-17 | 2025-10-23 | D2
Mockup 4 | https://github.com/COS420-F25/TeamD/issues/116 | Done | Medium | Non-technical | 2 |  | Xyrox47 |  | Chauncy O | 2025-10-17 | 2025-10-23 | D2
Mockup 2 | https://github.com/COS420-F25/TeamD/issues/114 | Done | Medium | Non-technical | 2 |  | NathHayes |  | Mason P | 2025-10-17 | 2025-10-23 | D2
Mockup 1 | https://github.com/COS420-F25/TeamD/issues/113 | Done | Medium | Non-technical | 2 |  | NathHayes |  | Mason P | 2025-10-17 | 2025-10-23 | D2
Create Quality checking policy within wiki | https://github.com/COS420-F25/TeamD/issues/95 | Quality Checking | Low | Non-technical | 1 |  | ChaunceyCon |  | Mason P | 2025-10-17 | 2025-10-23 | D2
Begin Work on UI (Coding) | https://github.com/COS420-F25/TeamD/issues/105 | Done | Low | Technical work | 3 |  | NathHayes |  | Josh V | 2025-10-17 | 2025-10-23 | D2
Create 5 Use Cases | https://github.com/COS420-F25/TeamD/issues/111 | Done | Low | Non-technical | 3 |  | ChaunceyCon |  | Josh V | 2025-10-17 | 2025-10-23 | D2
Architecture Design | https://github.com/COS420-F25/TeamD/issues/103 | Done | Low | Non-technical | 3 |  | PineCubed |  | Mason P | 2025-10-17 | 2025-10-23 | D2
Revise Requirements and Unique REQ IDs | https://github.com/COS420-F25/TeamD/issues/98 | Done | Low | Non-technical | 1 |  | Peazlez |  | Nathan H | 2025-10-17 | 2025-10-23 | D2
Fix Non-Functional Requirements | https://github.com/COS420-F25/TeamD/issues/110 | Done | Low | Non-technical | 2 |  | Xyrox47 |  | Nathan H | 2025-10-17 | 2025-10-23 | D2
Fix yourApp description from D0 | https://github.com/COS420-F25/TeamD/issues/96 | Done | Low | Non-technical | 1 |  | NathHayes |  | Chauncy O | 2025-10-17 | 2025-10-23 | D2
Fix User Stories | https://github.com/COS420-F25/TeamD/issues/97 | Done | Low | Non-technical | 1 |  | PineCubed |  | Xander W | 2025-10-17 | 2025-10-23 | D2
Revise Mockups 3 and 4 | https://github.com/COS420-F25/TeamD/issues/118 | Done | Low | Non-technical | 2 |  | ChaunceyCon |  | Xander W | 2025-10-17 | 2025-10-23 | D2
Fix Sprint Review | https://github.com/COS420-F25/TeamD/issues/99 | Done | Low | Non-technical | 2 |  | PineCubed |  | Nathan H | 2025-10-17 | 2025-10-23 | D2
Fill out the rest of the SRS | https://github.com/COS420-F25/TeamD/issues/102 | Done | Low | Non-technical | 5 |  | Peazlez |  | Chauncy O | 2025-10-17 | 2025-10-23 | D2
Create 5 Use Cases | https://github.com/COS420-F25/TeamD/issues/112 | Done | Low | Non-technical | 3 |  | Peazlez |  | Josh V | 2025-10-17 | 2025-10-23 | D2
Creating Classes (Coding) | https://github.com/COS420-F25/TeamD/issues/106 | Done | Low | Non-technical | 3 |  | Peazlez |  | Xander W | 2025-10-17 | 2025-10-23 | D2
Create description under diagram | https://github.com/COS420-F25/TeamD/issues/109 | Done | Low | Non-technical | 1 |  | ChaunceyCon |  | Xander W | 2025-10-17 | 2025-10-23 | D2
UI Mockups | https://github.com/COS420-F25/TeamD/issues/101 | Done | Low | Non-technical | 3 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 |  | Josh V | 2025-10-17 | 2025-10-23 | D2
Sprint Review | https://github.com/COS420-F25/TeamD/issues/100 | Done | Low | Non-technical | 1 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 |  | Josh V | 2025-10-17 | 2025-10-23 | D2
Revise Mockups 1 and 2 | https://github.com/COS420-F25/TeamD/issues/117 | Done | Low | Non-technical | 2 |  | Peazlez |  | Nathan H | 2025-10-17 | 2025-10-23 | D2
Description For document | https://github.com/COS420-F25/TeamD/issues/108 | Done | Low | Non-technical | 2 |  | Peazlez |  | Chauncy O | 2025-10-17 | 2025-10-23 | D2
Create list of Objects for Domain Model (Like the bottom page of linked examples) | https://github.com/COS420-F25/TeamD/issues/126 | Done | High | Non-technical | 2 |  | ChaunceyCon | 100% | Xander W | 2025-10-27 | 2025-10-31 | D3
Develop 3 Automated Tests for Feature 1 | https://github.com/COS420-F25/TeamD/issues/132 | Done | High | Technical work | 3 |  | PineCubed | 100% | Mason P | 2025-10-27 | 2025-11-07 | D3
Develop Feature 1: Git Integration | https://github.com/COS420-F25/TeamD/issues/130 | Done | High | Technical work | 5 |  | Peazlez, PineCubed | Mason (20%), Josh (80%) | Mason P | 2025-10-27 | 2025-11-07 | D3
Record 1-10 Minute Demo Video of our App Progress <FEATURE 1> | https://github.com/COS420-F25/TeamD/issues/137 | Done | High | Non-technical | 2 |  | PineCubed | 100% | Mason P | 2025-10-27 | 2025-11-07 | D3
Discuss list of objects for domain model | https://github.com/COS420-F25/TeamD/issues/136 | Done | High | Technical work | 1 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 | 20% each |  | 2025-10-29 | 2025-10-29 | D3
Sprint Review | https://github.com/COS420-F25/TeamD/issues/121 | Done | High | Non-technical | 2 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 | Xander (80%) 20% for everyone else. | Xander W | 2025-11-07 | 2025-11-07 | D3
Update ReadMe with new instructions for Feature 1 implementation | https://github.com/COS420-F25/TeamD/issues/142 | Done | Medium | Non-technical | 1 |  | PineCubed | 100% | Mason P | 2025-11-07 | 2025-11-08 | D3
Fill In description for Domain Model (After Issues 126/127) | https://github.com/COS420-F25/TeamD/issues/128 | Done | Medium | Non-technical | 2 |  | Xyrox47 | 100% | Nathan H | 2025-10-27 | 2025-11-07 | D3
Create Diagram for Domain Model (Once Task 126 is finished) | https://github.com/COS420-F25/TeamD/issues/127 | Done | Medium | Non-technical | 2 |  | Xyrox47 | 100% | Mason P | 2025-10-27 | 2025-10-31 | D3
Remove Dead Branch <update-readme> from TeamD Project | https://github.com/COS420-F25/TeamD/issues/140 | Done | Medium | Non-technical | 1 |  | Peazlez | 100% | Josh V | 2025-11-07 | 2025-11-09 | D3
Remove Dead Branch <react-app-setup> from TeamD project | https://github.com/COS420-F25/TeamD/issues/139 | Done | Medium | Non-technical | 1 |  | Peazlez | 100% | Josh V | 2025-11-07 | 2025-11-09 | D3
Develop 3 Automated Tests for Feature 2 | https://github.com/COS420-F25/TeamD/issues/133 | Todo / Sprint Backlog | Medium | Technical work | 3 |  | NathHayes | 100% | Xander W | 2025-10-27 | 2025-11-07 | D3
Setup Continuous Integration for Team D GitHub Repo | https://github.com/COS420-F25/TeamD/issues/129 | Done | Medium | Technical work | 2 |  | Peazlez | 100% | Josh V | 2025-10-27 | 2025-11-07 | D3
Update Product Backlog | https://github.com/COS420-F25/TeamD/issues/119 | Done | Low | Non-technical | 1 |  | Xyrox47 | 100% | Chauncy O | 2025-10-27 | 2025-11-07 | D3
Update/Revise Architecture Design Document | https://github.com/COS420-F25/TeamD/issues/125 | Done | Low | Non-technical | 2 |  | ChaunceyCon | 100% | Josh V | 2025-10-27 | 2025-11-07 | D3
Update/Revise SRS Document | https://github.com/COS420-F25/TeamD/issues/122 | Done | Low | Non-technical | 2 |  | Peazlez | 100% | Nathan H | 2025-10-27 | 2025-11-07 | D3
Complete Usability Testing Script | https://github.com/COS420-F25/TeamD/issues/135 | Done | Low | Non-technical | 2 |  | PineCubed | 100% | Mason P | 2025-10-27 | 2025-11-02 | D3
Update Sprint Backlog | https://github.com/COS420-F25/TeamD/issues/120 | Done | Low | Non-technical | 1 |  | ChaunceyCon | 100% | Mason P | 2025-10-27 | 2025-11-07 | D3
Update/Revise Use Case Descriptions (After Use Case Diagrams) | https://github.com/COS420-F25/TeamD/issues/124 | Done | Low | Non-technical | 2 |  | Peazlez | 100% | Chauncy O | 2025-10-27 | 2025-11-07 | D3
3 Usability Tests | https://github.com/COS420-F25/TeamD/issues/138 | Done | Low | Technical work | 2 |  | ChaunceyCon | 100% | Mason P | 2025-10-27 | 2025-11-07 | D3
Record 1-10 Minute Demo Video of our App Progress <FEATURE 2> | https://github.com/COS420-F25/TeamD/issues/134 | Todo / Sprint Backlog | Low | Non-technical | 2 |  | NathHayes | 100% | Chauncy O | 2025-10-27 | 2025-11-07 | D3
Develop Feature 2: Profile Customization | https://github.com/COS420-F25/TeamD/issues/131 | In Progress | Low | Technical work | 5 |  | NathHayes | 100% | Chauncy O | 2025-10-27 | 2025-11-07 | D3
Update/Revise Use Case Diagrams (Before Use Case Descriptions) | https://github.com/COS420-F25/TeamD/issues/123 | Done | Low | Non-technical | 2 |  | NathHayes | 100% | Josh V | 2025-10-27 | 2025-11-07 | D3
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 5> | https://github.com/COS420-F25/TeamD/issues/171 | Done | High | Non-technical | 1 |  | ChaunceyCon | 100% | Nathan H | 2025-11-10 | 2025-11-21 | D4
Develop 3 Automated Tests for Feature 2 | https://github.com/COS420-F25/TeamD/issues/133 | Done | High | Technical work | 3 |  | NathHayes | 100% | Xander W | 2025-10-27 | 2025-11-07 | D4
Develop Feature 2: Profile Customization | https://github.com/COS420-F25/TeamD/issues/131 | Done | High | Technical work | 5 |  | NathHayes | 100% | Chauncy O | 2025-10-27 | 2025-11-07 | D4
Create Example of Applying Design Pattern (description) <Feature 4> | https://github.com/COS420-F25/TeamD/issues/174 | Done | High | Technical work | 1 |  | Peazlez | 100% | Xander W | 2025-11-10 | 2025-11-21 | D4
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 4> | https://github.com/COS420-F25/TeamD/issues/170 | Done | High | Non-technical | 1 |  | Peazlez | 100% | Xander W | 2025-11-10 | 2025-11-21 | D4
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 6> | https://github.com/COS420-F25/TeamD/issues/168 | Done | High | Non-technical | 1 |  | NathHayes | 100% | Chauncy O | 2025-11-10 | 2025-11-21 | D4
Create Example of Applying Design Pattern (description) <Feature 6> | https://github.com/COS420-F25/TeamD/issues/172 | Done | High | Non-technical | 1 |  | NathHayes | 100% | Josh V | 2025-11-10 | 2025-11-21 | D4
<Website Navigation> (Set up Dummy pages) | https://github.com/COS420-F25/TeamD/issues/155 | Done | High | Technical work | 4 |  | Peazlez | 100% | Nathan H | 2025-11-10 | 2025-11-21 | D4
Set up Meeting with Dr Greg for project scoping | https://github.com/COS420-F25/TeamD/issues/144 | Done | High | Non-technical | 1 |  | ChaunceyCon | 100% | Mason P | 2025-11-10 | 2025-11-14 | D4
Sprint Review D4 | https://github.com/COS420-F25/TeamD/issues/147 | Done | High | Non-technical | 2 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 | 20% each | Chauncy O | 2025-11-21 | 2025-11-21 | D4
Create Example of Applying Design Pattern (description) <Feature 5> | https://github.com/COS420-F25/TeamD/issues/175 | Done | High | Non-technical | 1 |  | ChaunceyCon | 100% | Mason P | 2025-11-10 | 2025-11-21 | D4
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 3> | https://github.com/COS420-F25/TeamD/issues/169 | Done | High | Non-technical | 1 |  | Xyrox47 | 100% | Mason P | 2025-11-10 | 2025-11-21 | D4
Finish Feature 1 <Github Linking> | https://github.com/COS420-F25/TeamD/issues/164 | Done | High | Technical work | 3 |  | Peazlez, PineCubed | Mason (20%), Josh (80%) | Mason P | 2025-11-10 | 2025-11-21 | D4
Create Example of Applying Design Pattern (Sub-Diagram) <Feature 1> | https://github.com/COS420-F25/TeamD/issues/153 | Done | High | Non-technical | 2 |  | PineCubed | 100% | Mason P | 2025-11-10 | 2025-11-21 | D4
Create Example of Applying Design Pattern (description) <Feature 1> | https://github.com/COS420-F25/TeamD/issues/152 | Done | High | Non-technical | 1 |  | PineCubed | 100% | Mason P | 2025-11-10 | 2025-11-21 | D4
Assign Tasks | https://github.com/COS420-F25/TeamD/issues/154 | Done | High | Non-technical | 1 |  | Peazlez | Mason (80%), 20% everyone else | Chauncy O | 2025-11-10 | 2025-11-10 | D4
Create Design class/function diagram (Quality Check DCD document After completed) | https://github.com/COS420-F25/TeamD/issues/150 | Done | High | Non-technical | 2 |  | Peazlez | 100% | Xander W | 2025-11-10 | 2025-11-21 | D4
Create Example of Applying Design Pattern (description) <Feature 3> | https://github.com/COS420-F25/TeamD/issues/173 | Done | High | Non-technical | 1 |  | Xyrox47 | 100% | Chauncy O | 2025-11-10 | 2025-11-21 | D4
Record Team Progress Video | https://github.com/COS420-F25/TeamD/issues/159 | Done | High | Non-technical | 2 |  | PineCubed | 100% | Chauncy O | 2025-11-10 | 2025-11-21 | D4
Add deliverable documents to Repository | https://github.com/COS420-F25/TeamD/issues/143 | Done | Medium | Non-technical | 1 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 | 20% each | Chauncy O | 2025-11-10 | 2025-11-21 | D4
Develop Feature 5 <List/Search/Filter Portfolios> | https://github.com/COS420-F25/TeamD/issues/167 | Done | Medium | Technical work | 4 |  | ChaunceyCon | 100% | Xander W | 2025-11-10 | 2025-11-21 | D4
Develop Feature 3 <Resume System> | https://github.com/COS420-F25/TeamD/issues/166 | 30-60% done | Medium | Technical work | 4 |  | Xyrox47 | 100% | Chauncy O | 2025-11-10 | 2025-11-21 | D4
Assign sub tasks for DCD Features (After Scoping Meeting) | https://github.com/COS420-F25/TeamD/issues/151 | Done | Medium | Non-technical | 1 |  | Peazlez | 20% each | Nathan H | 2025-11-10 | 2025-11-21 | D4
Record Video Progress for Feature 3 | https://github.com/COS420-F25/TeamD/issues/157 | Done | Medium | Non-technical | 2 |  | Xyrox47 | 100% | Mason P | 2025-11-10 | 2025-11-21 | D4
Develop Feature 4 <Tagging System> | https://github.com/COS420-F25/TeamD/issues/165 | Done | Medium | Technical work | 4 |  | Peazlez | 100% | Josh V | 2025-11-10 | 2025-11-21 | D4
Create 2-3 Automated Tests for Feature 3 | https://github.com/COS420-F25/TeamD/issues/162 | Done | Medium | Technical work | 2 |  | Xyrox47 | 100% | Mason P | 2025-11-10 | 2025-11-21 | D4
Update/Revise Sprint Backlog | https://github.com/COS420-F25/TeamD/issues/146 | Done | Low | Non-technical | 2 |  | ChaunceyCon | 100% | Mason P | 2025-11-10 | 2025-11-21 | D4
Next Round of Usability Tests *****Extra Credit***** | https://github.com/COS420-F25/TeamD/issues/161 | Done | Low | Non-technical | 2 |  | ChaunceyCon, PineCubed | 100% Chauncey | Xander W | 2025-11-10 | 2025-11-21 | D4
Update/Revise Product Backlog | https://github.com/COS420-F25/TeamD/issues/145 | Done | Low | Non-technical | 1 |  | NathHayes | 100% | Josh V | 2025-11-10 | 2025-11-21 | D4
Update/Revise Domain Model Description and Object List | https://github.com/COS420-F25/TeamD/issues/149 | Done | Low | Non-technical | 1 |  | Peazlez, Xyrox47 | Mason (50%), Xander (50%) | Nathan H | 2025-11-10 | 2025-11-21 | D4
Update/Revise Domain Model Diagram | https://github.com/COS420-F25/TeamD/issues/148 | Done | Low | Non-technical | 1 |  | Peazlez, Xyrox47 | Mason (50%), Xander (50%) | Chauncy O | 2025-11-10 | 2025-11-21 | D4
Splice videos for progress video | https://github.com/COS420-F25/TeamD/issues/193 | Done | High | Non-technical | 2 |  | NathHayes |  | Chauncy O | 2025-11-24 | 2025-12-05 | D5
Sprint Review D5 | https://github.com/COS420-F25/TeamD/issues/187 | Done | High | Non-technical | 2 |  | ChaunceyCon, NathHayes, Peazlez, PineCubed, Xyrox47 | 20% each | Josh V | 2025-11-24 | 2025-12-05 | D5
Design Pattern for Design Technical Design | https://github.com/COS420-F25/TeamD/issues/189 | Done | High | Non-technical | 4 |  | ChaunceyCon |  | Mason P | 2025-11-24 | 2025-12-05 | D5
Finish Feature Search | https://github.com/COS420-F25/TeamD/issues/197 | Done | High | Technical work | 5 |  | ChaunceyCon |  | Nathan H | 2025-11-24 | 2025-12-05 | D5
Finish Feature Profile System | https://github.com/COS420-F25/TeamD/issues/190 | Done | High | Technical work | 5 |  | NathHayes |  | Chauncy O | 2025-11-24 | 2025-12-05 | D5
Work on website UI and design (match to our mockups) | https://github.com/COS420-F25/TeamD/issues/194 | Done | High | Technical work | 3 |  | Peazlez, PineCubed | 50% each | Xander W | 2025-11-24 | 2025-12-05 | D5
Portfolio Video | https://github.com/COS420-F25/TeamD/issues/199 | Done | Medium | Non-technical | 3 |  | NathHayes |  | Josh V | 2025-11-24 | 2025-12-04 | D5
Develop Feature 3 <Resume System> | https://github.com/COS420-F25/TeamD/issues/166 | Done | Medium | Technical work | 4 |  | Xyrox47 | 100% | Chauncy O | 2025-11-10 | 2025-12-05 | D5
Resume Video | https://github.com/COS420-F25/TeamD/issues/198 | Done | Medium | Non-technical | 3 |  | Xyrox47 |  | Mason P | 2025-11-24 | 2025-12-04 | D5
Finish Feature Resume System | https://github.com/COS420-F25/TeamD/issues/191 | Done | Medium | Technical work | 4 |  | Xyrox47 |  | Mason P | 2025-11-24 | 2025-12-05 | D5
Create 2-3 Automated Tests for Feature 6 | https://github.com/COS420-F25/TeamD/issues/179 | Done | Medium | Technical work | 2 |  | NathHayes | 100% | Xander W | 2025-11-24 | 2025-12-05 | D5
Search Video | https://github.com/COS420-F25/TeamD/issues/200 | Done | Medium | Non-technical | 3 |  | ChaunceyCon |  | Nathan H | 2025-11-24 | 2025-12-04 | D5
Tagging Video | https://github.com/COS420-F25/TeamD/issues/201 | Done | Medium | Non-technical | 3 |  | Peazlez |  | Josh V | 2025-11-24 | 2025-12-04 | D5
Develop Feature 6 <Portfolio System> | https://github.com/COS420-F25/TeamD/issues/180 | Done | Medium | Technical work | 4 |  | NathHayes | 100% | Josh V | 2025-11-24 | 2025-12-05 | D5
Finish Feature Tagging System | https://github.com/COS420-F25/TeamD/issues/192 | Done | Medium | Technical work | 4 |  | Peazlez |  | Xander W | 2025-11-24 | 2025-12-05 | D5
Revise Detailed Technical Design Document | https://github.com/COS420-F25/TeamD/issues/188 | Done | Low | Non-technical | 1 |  | PineCubed |  | Mason P | 2025-11-24 | 2025-12-05 | D5
Update/Revise Product Backlog | https://github.com/COS420-F25/TeamD/issues/185 | Done | Low | Non-technical | 1 |  | PineCubed |  | Chauncy O | 2025-11-24 | 2025-12-05 | D5
Usability Testing ****EXTRA CREDIT**** | https://github.com/COS420-F25/TeamD/issues/196 | Done | Low | Non-technical | 1 |  | ChaunceyCon |  | Mason P | 2025-11-24 | 2025-12-05 | D5
Update/Revise Sprint Backlog | https://github.com/COS420-F25/TeamD/issues/186 | Done | Low | Non-technical | 1 |  | ChaunceyCon |  | Josh V | 2025-11-24 | 2025-12-05 | D5
Test Plan ****EXTRA CREDIT**** | https://github.com/COS420-F25/TeamD/issues/195 | Todo / Sprint Backlog | Low | Non-technical | 1 |  |  |  |  | 2025-11-24 | 2025-12-05 | D5